## Slide 1
Marketing plan – XXXX
1. Aims
The service aims to improve the health and well-being of xx residents by encouraging them to make healthier lifestyle choices. The service will deliver evidence-based health improvement and behaviour change interventions to address the key health and wellbeing issues impacting the residents and communities. Through collaboration with stakeholders, the service aims to: · Enhance the health and wellbeing of XXXX residents. · Empower residents to take control of their health and achieve optimal wellbeing. · Reduce health inequalities across the population.

## Slide 2
3. Timeframes
There will be 3 phases: Phase 1: Welcome and Communicate about the new service and campaign - Stakeholder mapping, Inform the wider stakeholders about the new service - Communication to XXXX residents and partner agencies to promote the new service offer Asset and Channel development Resources Stakeholder packs Stakeholder communications Website Offline campaign resources Phase 2: Building service awareness A number of opportunities throughout year 1– link to national/local awareness days Phase 3: Evaluation Review and monitor performance with marketing activity included in each quarterly meeting/ report
2. Background
Following the award of the launch of the new xxxx service in xxxx, this marketing plan will outline the activities planned by the service to promote itself in the local community.

## Slide 3
5. Audience Strategy
Target Audiences |  |  | 
Professional stakeholders | Primary Care Networks: GPs, health care assistants, health check route, practice nurses, receptionists NHS Trust(s): Acute, Community, Mental Health, Substance misuse, maternity |  | Clinical Commissioning Group/ Integrated Care Board Community Pharmacies DWP Schools Family Centres Voluntary sector
XXXX residents |  |  | 
 |  |  | People aged 40+ particularly in areas of deprivation with high obesity rate People with conditions which put them at higher risk for Covid-19 BAME community People shielding

## Slide 4
6. Website
All online and offline content will point users to a website for resources to help them with their health and wellbeing journey. Health and wellbeing messaging on the XXXX website will be the main focus for traffic to the site, with client news stories, case studies, and quotes to be featured on the website news section (which will also be reflected on social media) Additional functionality around language and accessibility options will be explored and installed on the website to ensure accessibility by all members of the XXXX community There is a need to review search engine optimisation.

## Slide 5
7. Offline strategy
This is being used to complement the online strategy and is being targeted to priority audiences: Posters on bus stops – reach audiences in deprived areas XXXX Radio - reach an audience who do not engage with digital formats. Local magazines Voluntary groups Church and Faith organisations newsletters – Play an active role in the community GP newsletter School newsletters Local newspapers Foodbanks Libraries Cultural and Community Festivals Pre-natal groups and pregnancy outreach support services Community and Religious Centres Carers in XXXX Dentists Opticians XXXX Multicultural Groups Training events (L2, VBA) It is important to remember that not all our target audiences will be online, and therefore, additional tactics are required to ensure the most significant reach. Offline marketing will raise awareness of the service and create greater receptivity to messages and searches on social media for online audiences. Blending online and offline can strengthen the service's reach by making it visible in different environments when people need it. It will require lead-in times for booking sites and print production.

## Slide 6
8. Communication with key partners
Internal team We will ensure our core service team are aware of the key messages of the service offer, the schedule of phases and regular communication regarding feedback from clients, key partners and stakeholders XXXX Council We will request XXXX Council communicate the key campaigns and service information through the following means XXXX Council/NHS Trust newsletters Managers’ Brief/ blogs Stakeholder/partner newsletter (e.g. CCG/ ICB newsletter) Digital screens in the foyer (e.g. NHS Trust, GP surgeries County Hall) Partners and stakeholders – comms toolkit Public Health colleagues can share service details with comms leads in the council, NHS, and other stakeholders to engage them with the service offer. We will supply a communications toolkit to share assets, materials, and messaging with partners such as XXXX Council so they can adapt or deploy for their local audiences. This would include guidance, for example, on using the creative assets, including colour palette, typography and campaign imagery. Other channels We will also promote the campaign through: Collaborative meetings Primary Care Networks (PCNs) Voluntary sector Community groups

## Slide 7
9. Evaluation summary
The following KPIs will be monitored to inform the development of the awareness campaign and evaluate the success of raising awareness of the service. Professional Stakeholders Number of stakeholders (organisation and type) the information has been shared with these XXXX Residents Sign ups to the XXXX Service Hits to XXXX website Social media performance evaluation, which will include followers, likes, comments and shares to social media platforms In addition, we will reflect on: Did we achieve what we set out to do? What went well? What could have gone better? What would we improve if/when revisiting this or similar campaigns? Include thoughts/feedback from the client side to refine future phases of the campaign Timeframe: Regular monitoring (quarterly) and end-of-communication yearly report.

## Slide 8: Marketing and communications plan
Activity | Date | Comments
Work closely with XXXX to align marketing efforts with the new branding. | Feb 2025 | 
Finalise the logo, colour scheme, fonts, and visual identity. | Feb 2025 | 
Create brand guidelines to ensure consistency across all materials. | Mar 2025 | 
Develop templates for presentations, reports, social media, and printed materials. | Mar 2025 | 
Conduct stakeholder consultations to gather feedback on branding elements. | Feb 2025 | 
Produce branded merchandise such as banners, staff uniforms, and giveaways for events. | Mar 2025 | 
Branding Rollout - Finalisation

## Slide 9: Marketing and communications plan
Activity | Date | Comments
Develop an internal rollout schedule with specific milestones. | Feb 2025 | 
Conduct staff training sessions on brand messaging and visual identity. | Mar 2025 | 
Establish a phased public launch approach (teasers, soft launch, full rollout). | Mar – Apr 2025 | 
Coordinate with XXXX to ensure seamless brand integration. | Mar – Apr 2025 | 
Engage with community organisations and faith leaders to generate pre-launch buzz. | Mar – Apr 2025 | 
Branding Rollout – Launch timeline

## Slide 10: Marketing and communications plan
Activity | Date | Comments
Identify core messages tailored to different audience segments (families, older adults, minority groups, etc.). | Mar 2025 | 
Draft taglines and key service descriptions emphasising accessibility and health benefits. | Mar – Apr 2025 | 
Develop talking points for media appearances and community presentations. | Mar – Apr 2025 | 
Conduct A/B testing on different messages via social media and focus groups. | Mar – Apr 2025 | 
Translate key messages into multiple languages for inclusivity. | Mar – Apr 2025 | 
Branding Rollout – Key messaging development

## Slide 11: Marketing and communications plan
Activity | Date | Comments
Hold an internal presentation for stakeholders, partners, and key staff members. | Mar – Apr 2025 | 
Distribute digital brand packs, including logos, messaging guides, and email templates. | Mar – Apr 2025 | 
Set up email and newsletter announcements for internal teams. | Mar – Apr 2025 | 
Provide training on how staff should communicate the new brand in public engagements. | Mar – Apr 2025 & ongoing | 
Branding Rollout – Stakeholder and internal launch

## Slide 12: Marketing and communications plan
Activity | Date | Comments
Organise a press release and coordinate media outreach (local newspapers, radio, online news platforms). | Apr 2025 | 
Host a public launch event featuring key community leaders, residents, and healthcare professionals. | Q1 2025-2026 | 
Initiate a social media countdown campaign with daily teaser posts. | Apr-May 2025 | 
Launch paid promotional campaigns on Google Ads to enhance reach. | Apr-May 2025 | 
Distribute printed materials across key community locations. | Apr 2025 | 
Branding Rollout – External launch

## Slide 13: Marketing and communications plan
Activity | Date | Comments
Meet with XXXX and local community groups to align goals. | Feb-Apr 2025 | 
Identify partnership opportunities with schools, religious institutions, and non-profits. | Apr-May 2025 | 
Develop co-branded marketing materials that partners can distribute. | Apr-May 2025 | 
Set up monthly partner meetings to track engagement and identify areas for improvement. | Apr-May 2025 | 
Community engagement and outreach – Leveraging existing partnerships

## Slide 14: Marketing and communications plan
Activity | Date | Comments
Identify high-footfall locations for engagement (shopping centres, libraries, faith centres, schools). | Feb-Apr 2025 | 
Plan at least one major community event per quarter focused on different aspects of wellbeing. | Q1 2025-2026 | 
Distribute multilingual flyers, brochures, and promotional items at events. | Q1 2025-2026 | 
Collect sign-ups for email newsletters and service appointments at each event. | Q1 2025-2026 | 
Conduct on-site demonstrations of available health and wellbeing services. | Q1 2025-2026 | 
Community engagement and outreach – Community events

## Slide 15: Marketing and communications plan
Activity | Date | Comments
Establish relationships with religious leaders to spread service awareness. | Feb-Apr 2025 | 
Provide translated materials and culturally sensitive messaging for different communities. | Q1 2025-2026 | 
Organise information sessions in collaboration with faith leaders, ensuring accessibility. | Q1 2025-2026 | 
Create video content highlighting testimonials from different cultural communities. | Q1/ Q2 2025-2026 | 
Community engagement and outreach – Faith and cultural centres

## Slide 16: Marketing and communications plan
Activity | Date | Comments
Place posters in GP offices, libraries, community centres, grocery stores, and gyms. | Feb-Apr 2025 | 
Ensure posters and banners are engaging, easy to read, and visually appealing. | Feb-Apr 2025 | 
Refresh content every three months to keep messaging relevant and up to date. | Ongoing | 
Integrate QR codes in posters linking to the XXXX website for more information. | Feb-Apr 2025 | 
Community engagement and outreach – Community noticeboards and public spaces

## Slide 17: Marketing and communications plan
Activity | Date | Comments
Update XXXX with rebranded visuals and user-friendly navigation. | Feb-May 2025 | 
Ensure mobile-friendly and accessibility-compliant design (text-to-speech, high-contrast options). | Feb-May 2025 | 
Develop a FAQ page addressing common service inquiries in multiple languages. | Feb-May 2025 | 
Integrate a service booking system to facilitate easy appointment scheduling. | Q1 2025-2026 | 
Create a blog section featuring health tips, success stories, and expert insights. | Feb-May 2025 | 
Digital marketing and website strategy – Website development

## Slide 18: Marketing and communications plan
Activity | Date | Comments
Identify top search keywords related to health, wellness, and local services. | Feb-Mar 2025 | 
Develop SEO-friendly content for blog posts, service pages, and community resources. | Feb-May 2025 | 
Allocate the XXXX/month Google Ads budget strategically across demographics and interests. | Feb-May 2025 | 
Test different ad variations to optimise click-through and conversion rates. | Feb-May 2025 | 
Monitor ad performance and adjust strategies accordingly. | Feb-May 2025 | 
Digital marketing and website strategy – SEO and Google Ads

## Slide 19: Marketing and communications plan
Activity | Date | Comments
Build an email subscriber list via website sign-ups and community event participation. | Ongoing | 
Send monthly newsletters featuring success stories, health tips, and event announcements. | Ongoing | 
Segment email campaigns based on user interests and demographics. | Ongoing | 
Track open rates and engagement metrics to refine email content. | Feb-May 2025 | 
Digital marketing and website strategy – Email marketing

## Slide 20: Marketing and communications plan
Activity | Date | Comments
Rebrand existing social media accounts to align with new service identity. | Mar-Apr 2025 | 
Standardise profile pictures, cover images, and bio descriptions for consistency. | Mar-Apr 2025 | 
Ensure active presence on Facebook, Instagram, and X (Twitter) | Ongoing | 
Social media and content plan - Platforms

## Slide 21: Marketing and communications plan
Activity | Date | Comments
Develop a content calendar scheduling at least three posts per week. | Ongoing | 
Schedule posts in advance using the social media management tool Sprout Social | Ongoing | 
Adapt content strategy based on analytics and audience engagement trends. | Ongoing | 
Social media and content plan – Posting schedule

## Slide 22: Marketing and communications plan
Activity | Date | Comments
Service Introductions: Highlight different XXXX services via carousel posts and videos. | Ongoing | 
Health Tips: Provide actionable lifestyle advice related to nutrition, exercise, and mental health. | Ongoing | 
Event Promotions: Regularly update followers on upcoming workshops and outreach events. | Ongoing | 
Testimonials: Feature real success stories from service users in written and video formats. | Ongoing | 
Social media and content plan – Content themes

## Slide 23: Marketing and communications plan
Activity | Date | Comments
Use the national campaign branding to create localised posts and success stories. |  | 
Host campaign-specific outdoor clinics at busy locations such as shopping centres and parks. |  | 
National Campaigns
Date | Campaign | Overview | Partners/Touchpoints
Jan | Better Health | Annual Government campaign. Focuses in the NY, when people may be trying to improve their health | GPs, pharmacies, secondary care, workplaces, vape shops, mosques, workplaces
Feb/ May | Ramadan | Highlight that Ramadan is a good opportunity to lead a healthier lifestyle and offer culturally appropriate support. | GPs, pharmacies, secondary care, internal comms workplaces, vape shops, mosques, workplaces
March | No Smoking Day | Persuade people to quit smoking and to continue their attempts with Local services. Also, it is an opportunity to celebrate the success of non-smokers. | GPs, pharmacies, secondary care, internal comms workplaces, vape shops, mosques, workplaces

## Slide 24: Marketing and communications plan
Date | Campaign | Overview | Partners/Touchpoints
March | Nutrition and Hydration Week | Annual campaign to encourage people to have an awareness of their nutrition and hydration needs and encourage people to make healthier choices. | GPs, pharmacies, secondary care, internal comms workplaces, vape shops, mosques, workplaces
May | World No Tobacco Day | Annual WHO campaign raising awareness of smoking, tobacco and the health harms associated with it. | GPs, pharmacies, secondary care, workplaces, vape shops, mosques, workplaces
October | Stoptober | Encourage smokers to quit for 28 days. Also, an opportunity to celebrate. | GPs, pharmacies, secondary care, internal comms workplaces, vape shops, mosques, workplaces
September | World Heart Day | An annual campaign by the World Heart Federation raising awareness of heart health, scientific research and development and encouraging people to lead healthier lifestyles. | GPs, pharmacies, secondary care, internal comms workplaces, vape shops, mosques, workplaces
November | Mouth Cancer Month | Campaign to improve awareness of mouth cancer through education about signs and symptoms | NHS and private dentists, GP pharmacies, Oral Health Promotion Unit in the CCG, Mosques (highlighting smoking and shisha use), Islamic centres
Ongoing | Stop Before The Op | Improve awareness/ support patients before their elective operation. | Hospitals, GP surgeries, secondary care and outreach clinics

## Slide 25: Marketing and communications plan
Activity | Date | Comments
Design visually engaging multilingual flyers, posters, and brochures. | Feb-Mar 2025 | 
Ensure all printed materials align with brand guidelines and messaging. | Feb-Mar 2025 | 
Include QR codes that link to the XXXX website for digital interaction. | Feb-Apr 2025 | 
Develop easy-to-read leaflets tailored for different community segments (elderly, ethnic minorities, parents, youth). | Feb-May 2025 | 
Incorporate infographics to simplify complex health information. | Feb-May 2025 | 
Printed and offline marketing – Printed materials development

## Slide 26: Marketing and communications plan
Activity | Date | Comments
Identify key locations with high foot traffic (GP surgeries, pharmacies, libraries, supermarkets, places of worship, and community centres). | Feb-Apr 2025 | 
Partner with local businesses, health services, and XXXX to distribute materials. | Mar-May 2025 | 
Conduct leaflet drops in areas with lower digital engagement rates. | Mar-May 2025 | 
Organise outreach teams to distribute flyers at community events and marketplaces. | Mar-Jun 2025 | 
Ensure regular replenishment of printed materials at distribution points. | Ongoing | 
Printed and offline marketing – Distribution strategy

## Slide 27: Marketing and communications plan
Activity | Date | Comments
Identify high-traffic billboard locations for advertising key health campaigns. | Ongoing | 
Secure advertising spaces in local newspapers and magazines. | Ongoing | 
Collaborate with transport services to display ads on buses and shelters. | Ongoing | 
Explore opportunities for sponsorships on local radio stations. | Ongoing | 
Printed and offline marketing – Billboards and public advertising

## Slide 28: Marketing and communications plan
Activity | Date | Comments
Track the number of materials distributed and identify the most effective locations. | Ongoing | 
Collect feedback from community members on the usefulness of printed resources. | Ongoing | 
Adjust print strategies based on community feedback and service engagement data. | Ongoing | 
Printed and offline marketing – Measurement and evaluation

## Slide 29: Marketing and communications plan
Activity | Date | Comments
Organise four pop-up health clinic community events per year in different locations across XXXX (in addition to regular clinics). | Ongoing | 
Offer free screenings (blood pressure, BMI, diabetes, cholesterol checks). | Ongoing | 
Have on-site health advisors available for one-on-one consultations. | Ongoing | 
Provide sign-ups for XXXX programmes and follow-up support services. | Ongoing | 
Promote clinics in advance through social media, local press, and printed materials. | Ongoing | 
Events and outreach activities – Quarterly free health clinics

## Slide 30: Marketing and communications plan
Activity | Date | Comments
Secure a presence at major local events such as cultural fairs, religious gatherings, and seasonal festivals. | Ongoing | 
Set up interactive booths with health information, sign-up stations, and wellness activities. | Ongoing | 
Provide free giveaways such as branded tote bags, reusable water bottles, and health guides. | Ongoing | 
Conduct on-the-spot health quizzes and mini wellness workshops. | Ongoing | 
Events and outreach activities – Participation in community fairs and festivals

## Slide 31: Marketing and communications plan
Activity | Date | Comments
Partner with local employers to implement workplace health initiatives. | Ongoing | 
Offer lunch-and-learn sessions on nutrition, stress management, and smoking cessation. | Ongoing | 
Distribute digital and printed wellness toolkits for employees. | Ongoing | 
Distribute digital and printed wellness toolkits for employees. | Ongoing | 
Develop an incentive-based referral program to encourage employees to join IHWS programmes. | Ongoing | 
Events and outreach activities – Workplace wellness initiatives

## Slide 32: Marketing and communications plan
Activity | Date | Comments
Organise awareness walks for public health campaigns (e.g., Diabetes Awareness Month, Mental Health Awareness Week). | Ongoing | 
Conduct door-to-door community engagement efforts in priority neighbourhoods. | Ongoing | 
Hold special sessions at places of worship focusing on culturally relevant health topics. | Ongoing | 
Work with community influencers and leaders to host Q&A sessions on wellbeing topics. | Ongoing | 
Events and outreach activities – Targeted outreach campaigns

## Slide 33: Marketing and communications plan
Activity | Date | Comments
Track event attendance, engagement levels, and number of sign-ups | Ongoing | 
Gather qualitative feedback through surveys and focus groups. | Ongoing | 
Assess the impact of health screenings by following up with attendees. | Ongoing | 
Adjust event strategy based on participation data and feedback. | Ongoing | 
Events and outreach activities – Measurement and evaluation

## Slide 34: Marketing and communications plan
Activity | Date | Comments
Website traffic growth rate (monthly and quarterly). | Ongoing | 
Social media engagement (likes, shares, comments, reach, impressions). | Ongoing | 
Conversion rates from digital campaigns (Google Ads, emails, website visits to sign-ups). | Ongoing | 
Number of attendees at community events and workshops. | Ongoing | 
Number of printed materials distributed and feedback from users. | Ongoing | 
Referral rates from workplaces, schools, and community groups. | Ongoing | 
Demographic breakdown of service users to ensure targeted engagement is working. | Ongoing | 
Measurement and performance tracking – Key performance indications (KPIs)

## Slide 35: Marketing and communications plan
Activity | Date | Comments
Implement Google Analytics to track website performance and user behaviour. | Ongoing | 
Use social media insights tools to measure engagement trends. | Ongoing | 
Track event attendance and sign-ups through online registration forms and physical sign-in sheets. | Ongoing | 
Monitor client enquiries and feedback to identify recurring concerns. | Ongoing | 
Conduct community surveys to measure awareness and satisfaction levels. | Ongoing | 
Measurement and performance tracking – Data collection and reporting

## Slide 36: Marketing and communications plan
Activity | Date | Comments
Hold internal strategy meetings every quarter to review progress against KPIs. | Ongoing | 
Compare data against initial targets and adjust tactics where necessary. | Ongoing | 
Identify successful campaigns and replicate best practices for future initiatives. | Ongoing | 
Present findings to key stakeholders, including XXXX and local government representatives. | Ongoing | 
Measurement and performance tracking – Quarterly performance reviews

## Slide 37: Marketing and communications plan
Activity | Date | Comments
Use insights from data collection to refine marketing messages and strategies. | Ongoing | 
Test different advertising and outreach approaches to identify the most effective ones. | Ongoing | 
Address barriers identified in community feedback to improve accessibility. | Ongoing | 
Pilot new initiatives and expand successful ones in future marketing cycles. | Ongoing | 
Measurement and performance tracking – Adaptation and continuous improvement

## Slide 38: Timeline and action plan
Activity | Comments
Finalise branding elements and prepare promotional materials. | 
Begin outreach to community partners and stakeholders. | 
Launch the new website with SEO optimisation and content updates. | 
Develop content calendars for social media and digital marketing. | 
Create the first round of printed materials and distribute them to key locations. | 
Prepare for the public launch event. | 
Foundation and launch preparation

## Slide 39: Timeline and action plan
Activity | Comments
Execute the official launch event and coordinate media coverage. | 
Increase social media engagement with videos and community stories. | 
Conduct the first workplace wellness initiative. | 
Begin running Google Ads campaigns and adjust based on performance data. | 
Host the first quarterly free health clinic and assess impact. | 
Public rollout and engagement boost

## Slide 40: Timeline and action plan
Activity | Comments
Strengthen partnerships with local businesses and faith organisations. | 
Expand offline marketing efforts through billboards and public transit ads. | 
Increase participation in local festivals and fairs. | 
Assess impact of printed materials and adjust distribution strategy if needed. | 
Launch a targeted outreach campaign for specific demographic groups. | 
Expansion and community immersion

## Slide 41: Timeline and action plan
Activity | Comments
Conduct a full-scale review of all marketing activities. | 
Identify high-performing initiatives and prepare plans to expand them. | 
Gather comprehensive community feedback and refine future outreach strategies. | 
Develop recommendations for the next year’s marketing strategy based on data insights. | 
Review, optimise and scale up